## Work Breakdown Structure
Work Breakdown Structure
| Administration | Program | Attendees | Production | Partnerships | Marketing
1 | Event Concept | Program Schedule | Transport | Venue | Sponsors | Dervelop Marketing Plan
2 | WBS | MC | Parking | Catering | Benefits | Date Claimer
3 | Critical Path | Entertainment | Medical Assistance | Themeing/Décor | Contracts | Create event Flyer
4 | Financial Management | Speakers | Information Desk/ Ticket collection | Run sheets | Donor/ Data Managment | Printing
5 | Staff / Volunteers | Auctioneer | Place cards | Schedules | Hosting | Distribute Event Flyer
6 | Staff Briefing | Accommodation | Invited guests/ Sponsors | Briefings |  | Table host invites
7 | Rosters | Travel | Name Tags | Audio Visual |  | E-mail broadcasts
8 | Risk Management | Student to speak | Note Pads / pens | Sound |  | Photographer
9 | Thank You's | Chaplain to speak | Disabled | Lighting |  | Database
10 | Emergency | Chaplains to attend | Table lists | Staging |  | Response forms
11 | Insurance | On screen presentations | Support People | Signage |  | Media
12 | Communication | Thank-you's | Staff | Data Projection |  | Twitter
13 | Review | Sponsorship Acknowledgement | Special Requirements | Video |  | Facebook
14 | Regular Meetings | APRA |  | On-Site Management |  | Envelopes
15 |  |  |  | Cleaning |  | Program/ Menu
16 | [5 empty] | Chaplaincy Display table
17 | [5 empty] | Ticket confirmation
18 | [5 empty] | Mailings - hard copy
19
20
21

## Event Critical Path
2014 Event - Critical Path
| February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October
| 3_7 | 10_14 | 17_21 | 24_28 | 3_7 | 10_14 | 17_21 | 24_28 | 31_4 | 7_11 | 14_18 | 21_25 | 28_2 | 5_9 | 12_16 | 19_23 | 26_30 | 2_6 | 9_13 | 16_20 | 23_27 | 30_4 | 7_11 | 14_18 | 21_25 | 28_1 | 4_8 | 11_15 | 18_22 | 25_29 | 1_5 | 8_12 | 15_19 | 22_26 | 29_3 | 6_10 | 13_17 | 20_24 | 27_31
PUBLIC HOLIDAYS | [10 empty] | Easter 18 -21 | Anzac Day 25 | [6 empty] | Queen's Birthday 9 | [16 empty] | Labour Day 6
School Holidays
KEY EVENTS for 2014 | [15 empty] | CHAPPY WEEK
Key Dates for Event
MARKETING
Develop Marketing Plan
Date Claimer
Create Event Flyer
Printing
Distribute Event Flyer
Table Host Instructions/invites
Emails broadcasts
Photographer
Database
Response Forms
Media
Twitter
Facebook
Envelopes
Program / Menu
Chaplaincy Display table
Ticket confirmation
Mailings - hard copy
ADMINISTRATION
Event Concept
Critical Path
Financial Management/ Budget
Staff/ Volnteers
Rosters
Staff Briefing
Risk Management
Thank You's
Emergency
Insurance
Communication
Review
Regular meetings
PROGRAM
Program Schedule
MC
Entertainment
Key note Speaker
Auctioneer
Accomodation
Travel
Student to speak
Chaplain to speak
Chaplain to attend
On Screen presentations
Thanks you's
Sponsorship Acknowledgement
APRA
ATTENDEES
Transport
Parking
Medical Assistance
Information desk/ Ticket collection
Invited Guests/ Sponsors
Place cards
Name tags
Note pads/ pens
Disabled
Table lists
Support People
Staff
Special Requirements
PRODUCTION
Venue
Catering
Themeing/Décor
Run Sheets
Production Schedules
Briefings
Audio Visual (AV)
Sound
Lighting
Staging
Signage
Data Projection
Video
On site Management
Cleaning
PARTNERSHIPS
Source sponsors
Benefits
Contracts
Donor / Data Management
Hosting